## nRED TABLES
nRED TABLES — Physics Translation Dictionary nREDCube™ PRINCIPIA · Universal Principles of Status Change Management
Core Formula: S(A→B) = Δ(E·t) / ΔΩ where E = Energy/Effort · t = time · Ω = Impedance/Resistance
CATEGORY 1 — ENERGY (E) What drives status change forward
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Budget | Energy Potential | Financial | $ | Approved budget document | Final account | Total stored capacity
Actual Cost | Energy Released | Financial | $ | Invoice / claim | Certified payment | Energy consumed
Labour Budget | Energy Potential | Human | manhours | Resource plan | Timesheet summary | Human energy capacity
Labour Actual | Energy Released | Human | manhours | Timesheet / daily report | Final manhour report | Human energy consumed
Equipment hours (plan) | Energy Potential | Mechanical | machine-hours | Equipment schedule | — | Mechanical energy capacity
Equipment hours (actual) | Energy Released | Mechanical | machine-hours | Plant log | Equipment final report | Mechanical energy consumed
Energy reserve / contingency | Energy Reserve | Financial | $ | Risk budget allocation | Contingency drawdown log | Buffered potential — not yet released
Productivity rate | Energy Efficiency | Ratio | % or units/hr | Planned rate | Achieved rate | Released energy / planned energy
Momentum | Energy Accumulation | Trend | units/week | Rolling average log | — | Consecutive cubes of released energy
CATEGORY 2 — RESISTANCE (Ω) What opposes or slows status change — probabilistic, non-binary
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Weather (normal) | Resistance | Environmental | probability index | Met forecast | Met actual log | Routine — factored into plan
Extreme weather | Resistance | Environmental | probability index | EOT claim | Extension granted | Exceeds normal allowance
Ground conditions (unknown) | Resistance | Geotechnical | probability index | Geotech report | Site investigation actual | Discovered resistance, not designed
Bureaucratic delay | Resistance | Organisational | days | Submission date | Approval date | Internal process friction
Communication breakdown | Resistance | Informational | frequency | — | NCR / RFI log | Increases with team size
Risk (allocated, residual) | Resistance | Probabilistic | % probability | Risk register entry | Risk closed / triggered | Quantified potential resistance
Risk (unallocated) | Resistance | Unknown | undefined | — | Incident report | Not in model — pure resistance
Absenteeism | Resistance | Human | % labour lost | Planned roster | Actual attendance | Reduces available energy
Material shortage | Resistance | Supply chain | days delay | Delivery schedule | Delivery actual | Friction on energy release
Interface dependency | Resistance | Systemic | binary → probabilistic | Interface schedule | Interface completion | Between cubes or between parties
CATEGORY 3 — CONSTRAINTS (C) Hard boundaries — binary, non-negotiable
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Regulatory approval | Constraint | Legal/Compliance | binary (Y/N) | Application lodged | Approval certificate | Cannot proceed without — hard gate
Permit to work | Constraint | Safety | binary (Y/N) | PTW issued | PTW closed | Binary — no partial compliance
Hold point (ITP) | Constraint | Quality | binary (Y/N) | Inspection request | Inspection signed off | Inspector must witness — cannot bypass
Witness point (ITP) | Constraint | Quality | binary (Y/N) | Notification sent | Witness or waiver | Can proceed if witness waives
Contractual milestone | Constraint | Legal | date | Contract executed | Milestone certificate | Date-locked — triggers liquidated damages
Design freeze | Constraint | Technical | binary (Y/N) | Change freeze notice | — | No scope change permitted past this point
Jurisdictional law | Constraint | Legal | binary (Y/N) | — | — | External — cannot be removed by project
Safety critical sign-off | Constraint | Safety | binary (Y/N) | Safety case submitted | Safety acceptance | Engineering safety gate
Environmental clearance | Constraint | Legal/Environmental | binary (Y/N) | EIS submitted | EPA clearance letter | Legislative constraint
Approved drawings (IFC) | Constraint | Technical | binary (Y/N) | IFC issue | Construction on approved rev | Cannot build from non-IFC drawings
CATEGORY 4 — LEAKAGE (L) Energy consumed but not advancing status — waste within the system
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Rework | Leakage | Quality failure | $ or manhours | NCR raised | NCR closed | Energy spent twice on same status
Defect rectification | Leakage | Quality failure | $ or manhours | Defect list | Defect clearance | Post-completion rework
Abortive work | Leakage | Scope error | $ | Variation instruction | — | Work done, then reversed — pure leakage
Over-engineering | Leakage | Design inefficiency | $ | — | — | Energy beyond what status change required
Waiting time (within cube) | Leakage | GATE_SPACE micro | hours | — | — | Idle time inside an active cube
Idle plant / equipment | Leakage | Resource inefficiency | machine-hours | Plant on-hire date | Plant off-hire date | Energy cost with zero output
Meetings without decisions | Leakage | Informational | manhours | — | — | Energy spent, no status change
Duplicate work | Leakage | Coordination failure | manhours | — | — | Same task done by multiple parties
Data re-entry | Leakage | Systems failure | manhours | — | — | Digital leakage — no physical output
CATEGORY 5 — SCOPE RUPTURE (R) A status change that breaks the boundary of the cube — system boundary violation
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Scope change (approved) | Rupture → new cube | Formal variation | $ / scope unit | Variation order signed | New cube created | Rupture contained — absorbed into new cube
Scope creep (unapproved) | Rupture | Informal variation | $ / manhours | — | — | Energy leaving cube boundary unrecorded
Design change post-IFC | Rupture | Technical boundary | binary | Change request | Revised IFC issued | Rupture of design constraint boundary
Client instruction (undirected) | Rupture | Contractual boundary | binary | Instruction received | Variation lodged | May or may not be compensable
Discovery event | Rupture | Unknown boundary | undefined | — | EOT / variation claim | Unplanned rupture — cube boundaries violated
Technology change | Rupture | Innovation boundary | $ | — | Business case | Replaces existing cube structure
CATEGORY 6 — GATE_SPACE Visible idle resistance — cubes that exist but carry zero status-change energy
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Float / buffer | GATE_SPACE | Planned idle | weeks | Programme float | — | Intentional — planned idle resistance
Delay (unplanned) | GATE_SPACE | Unplanned idle | weeks | Last active cube date | Next active cube date | Unintentional — resistance made visible
Mobilisation gap | GATE_SPACE | Setup idle | weeks | Contract award | First site activity | Necessary but zero-output period
Procurement lead time | GATE_SPACE | Supply idle | weeks | Order placed | Goods on site | Cube exists — nothing moves inside it
Decision lag | GATE_SPACE | Governance idle | weeks | Submission date | Decision date | Resistance internal to client organisation
Seasonal shutdown | GATE_SPACE | Planned idle | weeks | Last working day | Return to site | Scheduled gap — zero energy flow
CATEGORY 7 — TIME (t) The X-axis — the only dimension that cannot be reversed
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Week | District Cube (time unit) | Default time slice | 7 days | Monday 00:00 | Sunday 23:59 | Default X-unit — can be day/fortnight
Programme start date | t₀ | Origin | date | Contract / kickoff | — | First cube in X-axis
Programme end date | t_x | Target | date | Contract / milestone | Completion certificate | Final cube boundary
Calendar float | GATE_SPACE | Planned idle time | weeks | Programme baseline | — | Intentional empty cubes
Extension of time (EOT) | t_x shift | Time boundary displacement | weeks | EOT claim | EOT grant | Contractual t_x pushed forward
Delay (unplanned) | Resistance → GATE_SPACE | Unplanned displacement | weeks | Last active cube | Next active cube | Unintentional t_x pressure
Deadline | Constraint (time) | Hard boundary | date | Contract | — | Cannot shift without contractual consequence
Monday COMMIT | Time boundary event | Weekly decision gate | binary | Week under review | COMMIT executed | The moment status is locked in history
Baseline programme | Energy path plan | Reference trajectory | date range per cube | Approved programme | — | The planned A→B path
Revised programme | Energy path update | Re-planned trajectory | date range per cube | Revision submitted | Revision approved | New planned path after displacement
CATEGORY 8 — SPACE (X, Y, Z axes) The three-dimensional grid in which status change occurs
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Week number | X-axis position | Time coordinate | integer (week) | — | — | Horizontal axis — the only irreversible one
Department / responsibility | Y-axis position | Accountability coordinate | organisational unit | Organisation chart | — | Who owns the cube
Subject / scope layer | Z-axis position | Scope coordinate | work package / system | WBS / PBS | — | What is being changed
Cube | District unit | Atomic status unit | 1 week × 1 Y × 1 Z | Gate IN criteria | Gate OUT criteria | Smallest indivisible unit of status change
Row (Y-slice) | Y-axis strip | Responsibility band | all Z at one Y, one X | — | — | The unit displaced on COMMIT if not done
Layer (X-slice) | Weekly review plane | Monday COMMIT target | all Y and Z at one X | — | — | The plane reviewed every Monday
Active cube | Cube with scope | Energy-carrying unit | binary | First scope entered | Last scope exits | Has Gate IN, Gate OUT, or Milestone
GATE_SPACE cube | Empty cube | Idle resistance unit | binary | First active cube | Last active cube | Between first and last active — idle made visible
Space filler (modes 0–4) | Visual GATE_SPACE marker | Display mode | 0/1/2/3/4 | — | — | 0=none, 1=between only, 2=+front, 3=+back, 4=all
Work package | Z-axis scope unit | Scope boundary | scope description | Scope register | Scope completion | Maps to one Z-layer
Production line | Z-axis group | Parallel scope band | set of Z-layers | — | — | e.g. 3 parallel train lines in QTMP
CATEGORY 9 — CUBE ANATOMY The internal structure of each cube
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Gate IN | Entry condition | Status precondition | binary (Y/N) | Prerequisite list | Gate IN signed | Top-left marker — must be met to start cube
Gate OUT | Exit condition | Status postcondition | binary (Y/N) | Completion criteria | Gate OUT signed | Top-right marker — must be met to close cube
Milestone S (standard) | Internal checkpoint | Planned progress marker | date | Programme | Achievement date | Standard milestone — schedule reference
Milestone C (contractual) | Constraint checkpoint | Contractual marker | date | Contract schedule | Milestone certificate | Hard contractual — triggers payment or LD
DONE state | Status confirmed | Binary completion | 0 or 100% | — | Monday COMMIT | Cube turns transparent — enters history
NOT DONE state | Status incomplete | Binary non-completion | 0% (treated as) | — | COMMIT → row shifts +1 week | Even 98% physical progress = 0 in status terms
Transparent cube | Historical status | Past light cone | binary | COMMIT executed | — | Visible border only — status locked in past
BoA (Basis of Approval) | Evidence store | Status proof | document set | Documents linked | — | Links cube to external databases / evidence
CATEGORY 10 — PEOPLE AND ROLES Human actors translated to physics functions
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Project owner / client | Energy source | Funds and authority | $ + decisions | Contract executed | Final payment | Origin of energy potential
Contractor | Energy converter | Executes status change | manhours + $ | Contract award | Practical completion | Converts potential energy to released energy
Subcontractor | Secondary energy converter | Partial scope | manhours + $ | Subcontract award | Sub-completion | Nested converter
Designer / engineer | Constraint definer | Sets technical boundaries | drawings + specs | Design brief | IFC issue | Defines what the cube must achieve
Regulator | Constraint authority | Enforces hard boundaries | binary decisions | Application lodged | Approval issued | External — cannot be negotiated away
Inspector / certifier | Gate keeper | Validates Gate OUT | binary sign-off | Inspection request | Certificate issued | Gate OUT cannot open without this role
Project manager | Energy coordinator | Routes and monitors energy | — | — | — | Does NOT change status — coordinates those who do
Sponsor | Energy authority | Releases energy reserves | $ approval | Business case | Budget approval | Controls contingency / Energy Reserve
Stakeholder | Resistance source | Adds constraint or friction | qualitative | Engagement plan | Sign-off / acceptance | Can be managed but not eliminated
CATEGORY 11 — DOCUMENTS AND DELIVERABLES Information objects translated to physics functions
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Contract | Constraint set | Legal energy boundary | binary | Signed contract | — | Defines what energy must achieve and by when
Specification | Constraint set | Technical boundary | binary | Issued for construction | — | Defines what DONE looks like
Drawing (IFC) | Constraint (active) | Construction boundary | revision number | IFC stamp | — | Cannot build from non-IFC
Drawing (non-IFC) | Leakage risk | Uncontrolled constraint | revision number | — | — | Energy released against wrong boundary = leakage
Programme / schedule | Energy path plan | Planned trajectory | date-cube map | Approved programme | — | Maps energy to cubes across X-axis
Risk register | Resistance catalogue | Probabilistic resistance map | probability × impact | Risk identification | Risk closed/triggered | Quantified resistance inventory
NCR (non-conformance report) | Leakage record | Quality failure evidence | binary | NCR raised | NCR closed | Documents energy that did not achieve status
RFI (request for information) | Resistance event | Information gap | days open | RFI submitted | RFI answered | Information resistance — delays energy flow
Variation order | Rupture document | Scope boundary change | $ / scope | VO submitted | VO approved | Formalises rupture — creates new cube
Inspection test plan (ITP) | Constraint map | Quality gate schedule | hold/witness/review | ITP approved | ITP complete | Maps Gate IN/OUT requirements for each cube
Completion certificate | Gate OUT (final) | Status change confirmed | binary | Application | Certificate issued | Ultimate Gate OUT for the entire programme
CATEGORY 12 — REPORTING AND MONITORING Measurement of energy flow and resistance — observational layer
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Progress report | Energy flow measurement | Periodic status snapshot | % or binary | Reporting period start | Report issued | Measures energy released vs planned
S-curve | Energy trajectory | Cumulative energy graph | $ or manhours vs time | Baseline programme | — | Planned vs actual energy release over X-axis
Earned value (EV) | Energy released (confirmed) | Value of completed work | $ | Work scope defined | DONE confirmed | Budget × % physically complete
Planned value (PV) | Energy scheduled | Expected energy release | $ | Baseline programme | — | What should have been released by t
Actual cost (AC) | Energy consumed | Cost incurred | $ | Invoices / timesheets | — | Energy spent regardless of status achieved
Schedule performance index (SPI) | Energy efficiency ratio | EV / PV | ratio (1.0 = on track) | — | — | <1.0 = resistance exceeding plan
Cost performance index (CPI) | Energy efficiency ratio | EV / AC | ratio (1.0 = on track) | — | — | <1.0 = leakage exceeding plan
Forecast at completion (FAC) | Projected total energy | Energy path projection | $ | Current CPI | — | AC + remaining budget adjusted for resistance
Dashboard / KPI report | Resistance indicator | Management visibility | various | — | — | Makes resistance and leakage visible to authority
Look-ahead programme | Near-term energy plan | 3–6 week horizon | cube map | Weekly COMMIT | — | Short-range energy routing — feeds Monday COMMIT
Variance report | Resistance record | Deviation from plan | $ / days | Baseline | Actual | Documents where resistance exceeded planned
GATE_SPACE ratio | Idle resistance index | % empty cubes between active | % | First active cube | Last active cube | e.g. 47% in QTMP — not efficiency, but visible idle
CATEGORY 13 — FINANCE AND PROCUREMENT Energy acquisition, storage, and transfer mechanisms
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Tender / bid | Energy potential offer | Proposed energy commitment | $ | RFT issued | Tender submitted | Offer to convert energy at a price
Contract sum | Energy potential (contracted) | Committed energy capacity | $ | Contract executed | — | Total stored energy authorised for release
Provisional sum | Energy reserve (undefined) | Unallocated energy capacity | $ | Contract executed | PS instruction issued | Placeholder — scope not yet defined
Prime cost item | Energy reserve (defined) | Allocated but unpriced | $ | Contract executed | PC instruction issued | Known item, unknown supplier price
Payment claim | Energy release request | Released energy invoice | $ | Work done | Claim submitted | Contractor requesting energy transfer
Progress payment | Energy transfer | Partial energy release | $ | Claim certified | Payment made | Energy flowing from owner to contractor
Retention | Energy hold | Withheld energy reserve | % of claim | Contract executed | Defects liability end | Held against future leakage / defect risk
Performance bond | Resistance buffer | Counterparty risk cover | $ or % | Contract executed | Bond released | Financial resistance absorber
Liquidated damages (LD) | Resistance penalty | Time boundary breach cost | $/day | Contract executed | EOT or LD triggered | Cost of failing to meet constraint (t_x)
Variation claim | Rupture energy request | Extra energy for scope rupture | $ | VO submitted | VO certified | Energy required for new cube created by rupture
Contingency drawdown | Energy reserve release | Reserve → active energy | $ | Risk event triggered | Expenditure approved | Reserve energy converted to released energy
Final account | Total energy reconciliation | Lifecycle energy summary | $ | Practical completion | Final certificate | Complete energy audit for the programme
CATEGORY 14 — SAFETY AND QUALITY Constraint enforcement and leakage prevention systems
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Safety management plan | Constraint framework | Safety boundary definition | binary (approved Y/N) | Plan submitted | Plan approved | Defines safety constraints for all cubes
Safe work method statement (SWMS) | Constraint (activity) | Activity-level safety boundary | binary | SWMS prepared | SWMS signed by workers | Gate IN for high-risk activities
Permit to work (PTW) | Constraint (hard gate) | Binary activity permission | binary | PTW requested | PTW issued + closed | Cannot start without — hard Gate IN
Toolbox talk | Resistance reduction | Team information briefing | frequency | — | Attendance record | Reduces human resistance / miscommunication
LTIFR | Resistance index | Lost time injury rate | injuries per 200k hrs | — | — | Measures human resistance to safe energy flow
Incident report | Resistance/Leakage record | Unplanned energy loss event | binary | Incident occurred | Report closed | Documents resistance or leakage event
Near miss report | Resistance warning | Near-failure signal | binary | Near miss occurred | Report closed | Early resistance signal — leading indicator
Quality management plan | Constraint framework | Quality boundary definition | binary | Plan submitted | Plan approved | Defines what DONE means for all cubes
Inspection test plan (ITP) | Constraint map | Gate IN/OUT schedule | hold/witness/review | ITP approved | ITP complete | Maps binary gates to specific cube activities
Hold point | Constraint (hard gate) | Binary inspection gate | binary | Inspection request | Inspector sign-off | Cannot proceed — Gate OUT locked by third party
Witness point | Constraint (soft gate) | Binary or waivable gate | binary | Notification issued | Witness or waiver | Can proceed if inspector waives — softer Gate OUT
NCR (non-conformance) | Leakage record | Quality failure evidence | binary | NCR raised | NCR closed | Energy consumed but status not achieved
Defect | Leakage (post-completion) | Post-Gate OUT failure | binary | Defect identified | Defect rectified | Gate OUT was incorrectly closed — energy lost
Audit | Resistance measurement | Systematic constraint check | score / findings | Audit scheduled | Audit report | Measures resistance compliance — not status
Concession / deviation | Constraint relaxation | Approved boundary shift | binary | Request submitted | Approved / rejected | Constraint moved — cube boundary adjusted
CATEGORY 15 — COMMUNICATIONS AND INFORMATION Information energy — the flow of data that enables or blocks status change
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
RFI (request for information) | Resistance event | Information gap | days open | RFI submitted | RFI answered | Open RFI = active resistance on cube
Submittal | Gate IN document | Pre-activity evidence package | binary | Submittal lodged | Submittal approved | Gate IN cannot open until submittal approved
Transmittal | Information transfer | Document delivery record | binary | Document issued | Receipt confirmed | Tracks information energy flow
Meeting minutes | Decision record | Energy direction confirmation | binary | Meeting held | Minutes issued + agreed | Undistributed minutes = information leakage
Action item | Micro-energy task | Discrete work unit | binary | Action assigned | Action closed | Sub-cube level — feeds cube Gate IN/OUT
Early warning notice | Resistance signal | Advance resistance alert | binary | Notice issued | Response received | Contractual mechanism to flag resistance early
Claim notice | Rupture signal | Boundary breach notification | binary | Event occurred | Notice served | Contractual trigger for variation / EOT
Correspondence register | Information flow log | Communication audit trail | count / days | — | — | Measures information resistance over time
BIM model | 3D constraint model | Digital scope boundary | revision | BIM brief | Model federated | Digital definition of what cubes must achieve
Data room / document control | BoA evidence store | Status proof repository | document count | Project start | Final archive | Feeds BoA — links evidence to cube completion
CATEGORY 16 — COMMISSIONING AND HANDOVER The final status change — from constructed to operational
Human Language Term | Physics Category | Sub-type | Unit | Gate IN Evidence | Gate OUT Evidence | Notes
Commissioning plan | Energy path plan | Pre-operational status map | binary | Plan approved | — | Maps final cubes before handover
Pre-commissioning | Gate IN (system) | System-level readiness check | binary | Construction complete | Pre-comm sign-off | Gate IN for commissioning cube
Commissioning | Status change (final) | Operational status activation | binary | Pre-comm complete | Commissioning cert | The cube where built → operational
Factory acceptance test (FAT) | Gate OUT (manufacture) | Off-site status confirmation | binary | Test schedule | FAT certificate | Gate OUT for manufacturing cube
Site acceptance test (SAT) | Gate OUT (installation) | On-site status confirmation | binary | FAT certificate | SAT certificate | Gate OUT for installation cube
Practical completion | Gate OUT (programme) | Construction status confirmed | binary | PC application | PC certificate | Programme-level Gate OUT
Defects liability period (DLP) | Post-completion resistance | Residual leakage window | months | PC certificate | DLP expiry | Period where leakage (defects) still expected
Final completion | Gate OUT (contract) | Contract status confirmed | binary | DLP expiry | Final certificate | Absolute Gate OUT — contract closed
As-built drawings | Historical record | Actual constraint map | revision | Construction complete | As-builts approved | Documents what status was actually achieved
O&M manuals | Operational energy guide | Future energy instructions | document set | Handover | Accepted by client | Guides future status changes in operational phase
Training (operator) | Energy transfer (knowledge) | Operational energy handover | manhours | Manuals available | Training complete | Human energy to operate the new status
Spare parts schedule | Energy reserve (operational) | Future resistance buffer | item list | Handover | Accepted | Stored energy for future maintenance cubes